ARL MSRC PET

Monthly Status Report

For the Period

May 1997

Army Research Laboratory

ARL DoD Major Shared Resource Center

DAHC94-960C-0010

Prepared For:

Army Research Laboratory

Aberdeen Proving Ground

Aberdeen, MD 21005-567

Prepared By:

High Performance Technologies Inc

31 May 1997

1. Programming Environment & Training (PET) Management

1.1 Accomplishments

1.2 Plans

1.3 Problems/Recommendations/Solutions

2. CCM CTA

2.1 Accomplishments

2.2 Plans

2.3 Problems/Recommendations/Solutions

3. CEA CTA

3.1 Accomplishments

3.2 Plans

3.3 Problems/Recommendations/Solutions

4. CEN CTA

4.1 Accomplishments

4.2 Plans

4.3 Problems/Recommendations/Solutions

5. CFD CTA

5.1 Accomplishments

5.2 Plans

5.3 Problems/Recommendations/Solutions

6. CSM CTA

6.1 Accomplishments

6.2 Plans

6.3 Problems/Recommendations/Solutions

7. FMS CTA

7.1 Accomplishments

7.2 Plans

7.3 Problems/Recommendations/Solutions

8. IMT CTA

8.1 Accomplishments

8.2 Plans

8.3 Problems/Recommendations/Solutions

9. SIP CTA

9.1 Accomplishments

9.2 Plans

9.3 Problems/Recommendations/Solutions

10. Programming Tools

10.1 Accomplishments

10.1.1 Rice University

10.1.2 University of Tennessee

10.2 Plans

10.2.1 University of Tennessee

10.3 Problems/Recommendations/Solutions

11. Outreach

11.1.1 Accomplishments

11.1.2 Plans

11.1.3 Problems/Recommendations/Solutions

12. Training

12.1 Accomplishments

12.2 Plans

12.3 Problems/Recommendations/Solutions

# Programming Environment & Training (PET) Management

## Accomplishments

- Met with Dr. Carl Henderson of the HEAT Center to discuss ARL MSRC cooperative agreement which will cover training facilities, certificate and degree programs.

- All the University partners have signed their contracts, except for Howard University. Howard has not responded to any of our queries and Ratheon E-Systems has retracted the contract offer.

- The ARL PET sponsored summer institute at Clark Atlanta University started 26 May and ends 6 June.  12 students from various HBCU/MI attended the summer institute.  7 of these will go on to AHPCRC's summer institute June 16 - Aug 16.  The other 5 will stay at CAU on an internship program, one of these 5 will do part of his internship at ARL this summer.  This is the first intern of our ARL PET internship program.

- Ginny worked with John Grosh to prepare an answer to Dr. Anita Jones’ concerns about the amount of PET funding being sent off site to the Universities.  Dr. Jones responded with a very positive note and is pleased with the ARL PET plans.

- Steve Matney assisted John Grosh in developing ARL PET thematic areas.  Produced 1st cut of slides outlining thematic areas for briefing on 5/29 to CTA leads.

## Plans

- Meet with Carl Henderson (HEAT Center) to further discuss cooperative agreement with HEAT Center and ARL MSRC on 9 June.

- Develop a white paper outlining goals, responsibilities and expectations for the ARL MSRC/HEAT Center cooperative agreement.  The draft white paper will be sent to the ARL MSRC senior managers.  The final white paper will be sent to the Harford Community College President for approval and then to the academic partners for review.

- We will spend some of the PET underrun budget on additional training equipment to put at the HEAT center.  ARL will be funding the parallel T1 from the HEAT Center to the ARL MSRC. for this link.

## Problems/Recommendations/Solutions

None to report.

# CCM CTA

## Accomplishments

- Dr. Margaret Hurley, whose seminars at ARL, ASC, and OSU were well received, will start as the ARL CCM onsite lead in July.

- Dr. Gerry Lushington will start as CCM Tracker at OSC for both ARL and ASC in August.  Dr. Lushington will also assist the CCM team with training, creating software tools, maintaining and developing a Web site for this area, and other needed tasks.

## Plans

- Continue with the Scope of Work set up in February, shifted to account for delays in getting personnel in place.

- Assess immediate needs for CCM CTA at ARL, contact major users, prepare a list of immediate needs and acquisitions needed for delivering the goals outlined in the 6 month ARL CTA plan, and establish Web presence for the ARL CCM CTA.

- We plan to present workshops which will be of interest for the ARL CCM user community.  At this moment, the best candidates for workshops include: a short course on using GAMESS quantum chemistry package, a intensive course for ACES II program package for correlated ab initio calculations, and a workshop on approaches in visualization for chemistry related computations.

## Problems/Recommendations/Solutions

- We need a clear procedure for processing requests for hardware, software, and services within this project.

# CEA CTA

## Accomplishments

## Plans

## Problems/Recommendations/Solutions

# CEN CTA

## Accomplishments

- Activity focused on planning and organizing future work with ARL.  Organizational meetings took place at NCSA to setup the interaction with ARL.  Dr. Paul Sotirelis (Senior Academic lead and the on-site Lead at ASC), agreed to work directly with Dr. Barry Perlman (Army, and CHSSI lead for CEN) to identify specific customer needs in the Army and at ARL, and to work together with Prof. Ravaioli, ARL CEN lead  at NCSA, to organize a CEN workshop under joint sponsorship of ASC and ARL.

- Dr. Sotirelis and Prof. Ravaioli met on May 24-27, at the International Workshop on Computational Electronics at Notre Dame University, and had several meetings to discuss interaction between ARL and ASC.  They also met with several DoD researchers and academic researchers working on DoD contracts, who are interested in CEN MSRC activities.  They also met with Dr. Gerald Iafrate, who will retire from his position as director of the Army Research Office in a few weeks, to gather advice on MSRC activities.

## Plans

- One of the immediate goals will be to identify the areas of DoD research where immediate impact could be made by bringing together the available resources.

- Work in the near future will focus on two specific themes:

- Definition of research and support activities for CEN at ARL.

- Staffing of the CEN support positions at NCSA.

## Problems/Recommendations/Solutions

None to report.

# CFD CTA

## Accomplishments

- The onsite CFD lead (Dr. Surya Dinavahi) has joined the CFD_CTA effective May 15.  He has spent a week at MSU understanding the MSU CFD tools and has attended the MSU conference on Differential Equations & Computational Simulations organized by the ARL CFD lead, Bharat Soni.

- Initial version of the PMAG (Parallel Multiblock Adaptive Grid system) has been completed and exercised for configurations of interest to ARL.  This system will be incorporated on the PCA and Origin 2000 at ARL in June.

- A joint collaborative project (CFD-03) between ASC and ARL has been formulated to explore turbulence models pertinent to combustion, chemically reactive and propulsion CFD applications.  Dr. Mike Nusca of ARL and Dr. Balu Sekar of ASC will be involved in this project with Dr. Warsi and Dr. Dinavahi.

- A project to combine BOXLIB from Lawrence Livermore with the parallel library developed by Nikos Chrisochoides of Notre Dame to address AMR (Adaptive Mesh Refinement) applications has been developed (part of CFD-02).

- A project to numerically simulate electro-physiology related characteristics on hearts is being carried out by Dr. Zoltani of ARL. CFD_CTA is now playing a role in providing assistance in girding related needs and in establishing a collaborative working relationship with Dr. Keener of University of Utah.  A visit to University of Utah will take place in June to explore possible collaboration.

- A training course on Grid Algorithms and Tools was offered at ARL.  Dr. Bob Meakim (Army ,NASA/Ames - Chimera technology), Dr. Dave Belk (Eglin AFB - BEGGAR Code for Overset methods), Dr. Nikos Chrisochoides (Notre Dame - Parallel Library for grids) and Bharat Soni gave lectures and demonstrations in this course.  A class of grid configurations of interest to ARL were created  for demonstrations.

- A visit to Army Cardrock facility was taken to contact CFD personnel and explore further outreach and collaborative activities.

- Steve Matney met with Jay Boris (CFD CTA lead) to update him on ARL PET CFD efforts.

## Plans

- Develop a short course on PARALLEL CFD in collaboration with ASC.  This course will be offered in July in the Washington, DC area to attract more CFD users.

- Establish ARL as a beta site for the CHSSI code on Chimera Technology being developed at the Army, NASA/Ames center.  Develop improved algorithms to perform hole cutting, marching grid near solid components, interpolation/search needed to evaluate donor cells and associated HPC parallel schemes.

- Exercise parallel library tool : PETSc from Argonne in view of ARL applications(CFD02).

- Participate and present at the DOD HPC User's workshop in San Diego.

- Establish a collaboration between University of Utah and ARL in computational electro-physiology area (Dr. Zoltani: PI).

- Expand outreach activity to other Army and DOD facilities.  In particular, Redstone Arsenal in Huntsville, NRL, David Taylor Ship facility and others.

- Form a formal TWG and coordinate with Jay Boris, DOD CFD lead, on CFD CTA activities.

- Establish a WWW tracking site and plan a CFD Newsletter in collaboration with ASC.

## Problems/Recommendations/Solutions

None to report.

# CSM CTA

## Accomplishments

- Met with CEWES PET lead and CEWES CSM lead to discuss joint MSRC projects.

- Met with Kent Kimsey (CSM CHSSI lead), Fouad Armad (ARL CSM lead located at NCSA) and John Grosh to discuss ARL CSM projects.

## Plans

## Problems/Recommendations/Solutions

None to report.

# FMS CTA

## Accomplishments

- Recruiting efforts are underway for the FMS onsite position.  Ads have been placed in various Usenet newsgroups, mailing lists, the Baltimore Sun and the Washington Post.  Responses are starting to come in.

- Kelly installed all of the Army Experiment III simulation logs data on “eckert”.  Army Experiment III (AE3) was a multi-node force-on-force simulation exercise held in September - October 1996.  ARL architectured a heterogeneous simulation network and collected simulation data packets and network traffic data.

- Steve Matney met with Bill Smith of NRL for discussions on FMS.  Bill will be sitting in for Bob Wasilausky at the PET/CTA leaders meeting.

- Dr. Wojtek Furmanski is leading our work on advanced web technologies for FMS.  He and his students are presently focusing on developing a more thorough understanding of related work in this area by other groups.

## Plans

- Gang Cheng, Geoffrey Fox, and Wojtek Furmanski will visit ARL 5-6 June 1997 to discussion advanced web and database technologies for FMS, IMT, and related activities at ARL.

- David Bernholdt, Geoffrey Fox, and Wojtek Furmanski will attend the DoD HPC User's Group Meeting in San Diego at the end of June.  We expect to split Bernholdt and Fox's costs among the three MSRCs. Furmanski's costs will be covered by ARL.

- Syracuse University will analyze the simulation and network data from Army Experiment III, which will lead to a paper that will provide information to the simulation community to decide if they should choose to continue to support DSI.

## Problems/Recommendations/Solutions

None to report.

# IMT CTA

## Accomplishments

- Met with OPTEC representatives to discuss fast data retrieval and archive project.

- Clark Atlanta came up for the day and met with Virtual Proving Ground Players from ARL, Aberdeen Test Center, and TECOM.  The government folks are going to prioritize their needs/projects and get back to ARL PET.

## Plans

- A meeting with Aberdeen Test Center and Pax River will be held in June to discuss a collaboration effort in Tri-service data sharing.

- OPTEC is looking for help to do network architecture analysis of the OPTEC and TECOM networks.  OPTEC needs to interoperate with the TECOM network in the near future and needs to learn about and understand the issues which must be addressed in order to accomplish this.  This task does will not fall under PET, is likely to be short term (about 3 months for the analysis), and then may become a larger task to do the network implementation.

## Problems/Recommendations/Solutions

None to report.

# SIP CTA

## Accomplishments

- Steve Matney attended a morning meeting at Rome Labs with Grosh and Joe McCaffrey (CWO lead), Joe Matusic (NAVO Northrop Grumman), Dave Rodkey and Gary Stolovy from ARL, Stan Ahalt (Ohio State; ARL SIP university lead).  This meeting was an organizational meeting for the afternoon meeting with Rich Linderman, the SIP CTA lead.

- Steve Matney attended an afternoon meeting at Rome Labs with above plus Bob Sinkovits (SDSC), Cherri Pancake (Oregon State via phone), Rich Linderman (DoD CHSSI lead for SIP), Mark Linderman, Ralph Kohler, Zen Pryk (all from Rome Labs).  Topics of discussion included:

- Briefing the SIP CTA lead on the ARL and NAVO PET programs.

- Projects/software that would most benefit the SIP user community.

- Methods that can be used to support new SIP HPC users.

- Future workshops.

- Steve Matney met at NRL with NRL SIP users to discuss their general needs.

## Plans

## Problems/Recommendations/Solutions

None to report.

# Programming Tools

## Accomplishments

- Jeff Durachta visited Andrew Grimshaw at University of Virginia to discuss HPCMO-wide Queuing System project. This will be a joint MSRC project.

- Steve Matney and Jerry Clarke started developing a “Crisp Research Plan” for DICE.

### Rice University

- Chuck Koelbel hosted a meeting of PET programming tools on-site people at Rice University.  Attendees included Ken Kennedy Chuck Koelbel, Danny Powell (all from Rice), Clay Breshears (CEWES), Jeff Durachta (ARL), Terry Clark (ASC), Dan Nagle (Nichols, CEWES).  All three sites are eager to coordinate on providing software, expertise, and training.  Most popular projects among the personnel were small, special purpose tools that could be helpful in the grunge work of code porting.  Larger systems such as debuggers were seen as vital, but not practical to develop given budget constraints.  Training will be challenging due to the diversity of audiences within each MSRC and between MSRCs.

- The UltraSparc workstations have been ordered, to be paid for jointly by all three MSRCs.  Delivery and installation are expected during June.  These will be used to support DOD work by Charles Koelbel and Ehtesham Hayder.

- Ehtesham Hayder accepted a full-time DOD Modernization position (funded jointly by ARL, CEWES, and ASC) at Rice.  He will start October 1.

### University of Tennessee

- Jeff Durachta visited the University of Tennessee.

- Did presentations and demonstrations of the following research projects for Jeff Durachta and Terry Clark from ASC: ScaLAPACK NetSolve and PVMPI.

- Jeff attended the SPEC/HPG and PARKBENCH meetings hosted by University of Tennessee and SPEC.

- Jeff Durachta met with Jack Dongarra, Shirley Browne, and Chuck Koelbel to discuss ARL PET Programming Tools.

- Held a planning meeting of all our staff who will be working on ARL PET this summer and assigned tasks for the ARL statement of work.  We will coordinate carrying out the statement of work with Jeff Durachta, the ARL on-site programming tools lead.

- Started setting up accounts on the ARL SGI PCA and Origin 2000.

## Plans

- Jeff will develop a research plan for the HPCMO-wide Queueing System project.

- Steve Matney and Jerry Clarke will finish up the DICE research plan

### University of Tennessee

- Compile monthly technology tracking reports.

- In coordination with Jeff Durachta and the NHSE, evaluate and test software libraries and tools relevant to ARL MSRC users and applications, and work with software authors to make selected tools available to ARL MSRC users.

- Install, test, and time the latest versions of LAPACK, BLACS, and ScaLAPACK on ARL MSRC platforms.

- Provide up-to-date performance data for the ARL MSRC by carrying out the following tasks:

- Port, test, and time selected PARKBENCH codes on ARL MSRC machines.

- Interpret and specialize benchmark results for ARL applications.

- Implement at ARL a performance database similar to the University of Tennessee’s Performance Database Server to give ARL users access to performance results.

- Customize and support the NHSE Repository in a Box (RIB) toolkit for ARL software repositories.

## Problems/Recommendations/Solutions

None to report.

# Outreach

### Accomplishments

- Working on ARL MSRC outreach video.

### Plans

- Continue plans on newsletter and brochures

### Problems/Recommendations/Solutions

- We have been planning and discussing ideas for a quarterly newsletter, however, we've been unable to execute because we do not have the staff.  We have been interviewing for a technical writer to help produce the newsletters and brochures.  A photographer and graphics artist is also necessary on a as-needed basis.  A plan will be developed to address the  additional resources needed to support outreach endeavors.

# Training

## Accomplishments

Presented the following courses in May

- EnSight Basic Training for CFD and CSM

- EnSight Intermediate training for Computational Fluid Dynamics (CFD)

- EnSight Intermediate training for Computational Structural Mechanics (CSM)

- EnSight Animation Training

- Introduction to the DoD MSRC HPC Environment

## Plans

- Courses planned for June

- IMT Seminar

- Introduction to the Global Resource Director (GRD)

- Courses planned for July

- SGI Origin Parallel Programming

- The Application of Matrix Solvers to Computational Electromagnetics

- Courses planned for August

- Applications of Advanced Porting Topics

- CCM ACIS 2 Workshop

## Problems/Recommendations/Solutions

None to report