1.	Focused Effort Title:	Computational Science and Information Technology: Curriculum and Technology

2.	Organization:		Florida State University

3.	Thematic Area:		HPC Training and DoD User Productivity

4.	PI Name:			Prof. Geoffrey Fox

5.	E-Mail:			 gcf@cs.fsu.edu

6.	Telephone:		(850) 644-4587

7.	Fax:			(850) 644-0098

8.	Statement of Work:

We describe a new curriculum (Computational Science and Information Technology) being developed at Florida State University. The curriculum consists of four courses:

- Computational Science I

- Computational Science II

- Applied Information Technology I

- Applied Information Technology II

Each course is described in the Appendix. We argue that it could be of particular value to HBCU/MI's and to DoD scientists and engineers. This value will be enhanced if the curriculum is made available by distance education technology. In this project, we take this basic thesis and we investigate its value to the ERDC Graduate Institute. We do this in a way that will test technology that is being developed in other focused efforts. This semester we taught a class to several sites including JSU and the ERDC Graduate Institute. We used TangoInteractive technology and although adequate, the class was disappointing in its lack of interactions between students and teacher. When the class was given at ERDC there were many interactions with students. When giving the class from Syracuse or Tallahassee, there were essentially no questions from any remote site. We have proposed in other focused efforts, a different strategy from Tango, which involves a mix of synchronous and asynchronous interactions with lectures available in SMIL format for students to peruse before tutorial sessions held synchronously. We have also proposed developing novel applications of hand-held devices.

9.	Deliverables:

- September 2000: Technology Framework and Curriculum Design

- December 2000: Graduate class developed and adapted for ERDC Graduate Institute

- January-April 2001: Delivery of prototype class at ERDC Graduate Institute

- Contribution to PET Annual Report

- Written progress reports in June and December 2000

- Presentations for PET Midyear and Annual Reviews

- Final Technical Report