10 Feb. 1998

Status and Progress Report

On the

FMS-2  Simulation Leveraged Acquisition Test and Evaluation

Through January 1998

From: 	Henry Ng, Code 5585, Naval Research Lab

To:	Robert A Wasilausky, Code 404

# Tasks Completed

- Finished the CTP matrix for the TEMP addendum update.

- Completed and submitted the contract for SAIC to continue support the CHSSI development work to NRL contracting department.

- Darrin West presented a technical paper on FMS2 model framework at the Winter Simulation Conference in San Diego, CA on January 14, 1998.

# Tasks Started

- Received a letter from the Army Testbed Product Office (TPO) to request a copy of the FMS-2 framework for use in the Extended Air Defense Testbed (EADTB) program.

# Tasks in Process

- Continue to implement the battlefield visualization program.

- Implementation of the Modeling Framework is continuing.

- Implementation of the Data Management system is continuing.

- Design and implementation of Navy and Air Force asset models is continuing.

# Narrative

This monthís main efforts were devoted to:

## Updating the TEMP Addendum.

- The CTP matrix for the FMS2 TEMP addendum was completed. It includes the target values, minimum required values/threshold and decision supported for each testing phase. The critical technical parameters includes : efficient scaleable HPC performance improvement over current system; port software across different DOD HPC platforms; and produce valid, robust software.

## Model Framework

- A letter was received from the Army Testbed Product Office (TPO) in Huntsville, Alabama. They expressed interests in FMS2 model framework. They believe our implementations of event management in FMS2 and TEMPO techniques are of particular interest for software reuse to improve the performance of their Extended Air Defense Testbed (EADTB) program processes. They would like to request a copy of the framework to experiment with. In return, any extensions made by them to our basic model framework will be made available to FMS2. The TPO understands that our model framework was originally developed and funded by HPCMO CHSSI program and will happy to acknowledge this fact in any future publications and/or deliveries of EADTB software. A copy of FMS2 framework code will be sent to TPO program office.

- A technical paper describing FMS2 model framework was written and submitted for the Winter Simulation conference sponsored by The Society for Computer Simulation. Darrin West presented the paper at the conference which was held in San Diego, CA on January 14th, 1998. It was very well received.

## Model development

Model development is continuing. The major areas of implementations were formulated for this FY. The mission planning in NASM/AN and the tactical decision areas have the highest priority. The battlefield visualization program is improving to provide a better insight on the simulation results. In addition, preparation work to fine tune the model framework for the alpha testing is underway.

# Financial Summary (as of 12/97)

* Air Force matching fund

# Schedule/ Milestones

The milestones listed here revolve around builds that incrementally increase the functionality of the system. Each build contains time for a review of new requirements and modifications to the architecture (design). This iterative approach reduces the risks introduced by new modeling and performance requirements.  In addition, there is no single integration and test phase- it is spread out among the builds. Until we have reviewed the Air Force requirements, these build dates are approximate based on our current understanding of their requirements.

Millstone Name             		Description 	Target Date

-----------------------------------+------------------------------------------------+------------------------

Preliminary Architecture 	Review of preliminary architecture.    		Aug 14,  96

Review

Data Management		Completion of prototype based on       	Sept 30,  96

Prototype 			Preliminary Architecture.

Requirement Review          	Review of newly injected requirements   	Dec 1,  96

Architecture Review         	Review of architecture                   		Feb 1,  96

Build 1                     		Synthetic Environment and

Modeling Framework                      		June 1, 97

Build 2                     		Low Fidelity Model Port                 		Oct 1, 97

Build 3                     		Scalability and performance

testing and enhancement                 		Feb 2, 98

Build 4                     		Data Management  and Synthetic

Environment Enhancements                	June 1, 98

Build 5                     		High Fidelity Models                    		Oct 1, 98

Build 6                     		Scalability and performance testing

and enhancement                         		Feb 1, 99

Beta Release                	Analysis and experimentation Tools      	June 1, 99

Release                     		Tested as per SDP                       		Sept 30, 99

# Software Trouble Reports

None

# Problems

None

# Concerns

None

# Issues

During our CHSSI program review at NRaD on Nov. 12th, we discussed the FMS2 Master Test/Review Schedule. After a careful review of the work and our plan, we feel it is better and easier if we can change the dates as we proposed in November -- i.e. Alpha test -- 3QFY98; Beta test -- 1QFY99 and IOT&E --4QFY99. It is because we need a little more time to incorporate the Air Force requirements into FMS2. It  has costed us some time when we did the teaming with the Air Force and the modification for supporting Simulation Based Design applications early the year. We would feel more comfortable if the schedule is changed, especially the Beta and IOT&E test.