April 7, 1998

TO:  CTA and PEI Leads

FR:  E. J. Grabert, NCSA Academic Lead, ARL PET

RE:  Pet Year 3 Projects Development

At the ARL PET Year 2 Mid-Year Review you were introduced to the ARL PET approach to planning and executing projects for Year 3 and beyond.  This approach is intended to serve as a bridge between academic and DoD environments and provide the framework for planning, managing, and executing work addressing DoD requirements.

The overriding objective(s) of this framework is to apply the discovery and training accomplished in the PET program Years 1 and 2 to problem sets of a larger number of users, and to continue the team efforts in Outreach, Training and Productivity Enhancement.

Of course, there is still a continuing requirement to discover/develop and implement existing and emerging technologies.  This need will continue to be critical for the execution of the CTA work plans.

The approach we are taking is to ask you to look at planning a multi-year effort.  Typically, within DoD, the R&D community looks beyond the current year in proposing research objectives.  While the work that PET is undertaking is not R&D in the typical sense, the PET program lends itself well to the R&D model of management.

This approach will not eliminate the need for annually executable contracts, but will provide to the partners the direction for PET for three years, enabling them to prepare and execute a comprehensive and coherent multi-year plan for Technology Transfer to the DoD scientists and engineers.  Further, this approach provides for building long-term collaborative efforts.

The mechanism for developing this three-year plan is the work package, which consists of multiple projects running parallel, sequentially, or both.  Over time, the work package, as a framework for projects, will remain and change only incrementally as the program moves into the future and project successes are realized.  Of course, the active part of the work package is the project.  Projects define (1) users to be supported, (2) objectives to be achieved, (3) collaborative efforts, (4) resources required for execution, and (5) start and end points.  The aggregation of projects objectives define the work package and how the work package supports accomplishment of thrust area goals.

At the Mid-Year Review, three thrust areas were presented: Test & Evaluation, Automatic Target Recognition, and Weapons and Warfighter Systems Design.  These areas are broad and overarching and at the moment ill defined.  Almost certainly, there are more challenges than PET is prepared to undertake without substantial growth.  As the PET program matures and the role of ARL PET in the thrust areas becomes better defined, the projects planned for Year 3 and beyond should have objectives that are better focused in a particular area.

Project conception, development and execution should reflect a long-term application of a critical mass of resources to address significant DoD issues in the thrust areas.  The DoD issues are not yet fully defined, but as we close out Year 2 and move into Year 3, the significant DoD issues in the thrust areas that PET addresses will unfold.

Until then, the guidance for developing Year 3 proposals is to develop Work Packages and Projects documents that specifically address end user needs as currently known.  For example, if an end user in the T&E community is attempting to understand why a water tanker has a tendency to turn over, PET can help the user to make use of HPC and visualization tools and techniques to study and evaluate the data.

Generally, a CTA or PEI will contribute projects to just one Work Package.  However, the possibility that CTA and PEI efforts may span multiple Work Packages should not be overlooked.  The Work Packages in conjunction with the Thrust Areas represent the Strategic level for PET.  The component projects within the work packages represent the Tactical level for PET.  For purposes of setting this approach in place it can be expected that there will actually be 12 to 16 Work Packages.  The matrix below is a start and may or may not reflect the total number of Work Packages expected, but should provide an indication of the Thrust Areas that appear to be most appropriate to the CTA/PEI for project development.

T&E		ATR		WPNS

CCM                                        X                                                     X

CFD                                         X                                                     X

CSM                                        X                                                     X

FMS                                         X

IMT                                          X

SIP                                           X                      X                           X

S-V & DF                                X                      X                           X           *

I-C                                           X                      X                           X           *

Perf & Integr Tools                 X                      X                           X           *

Distance Lrng Tech                 X                      X                           X           *

*   These PEI (crosscutting technology teams) would necessarily contribute to work packages for which a CTA has primary lead.  However, there may be occasion when PEI have stand-alone work packages and projects.  For example, where a PEI is discovering and/or developing a technology that is applicable to several areas and the PEI is pushing the technology to the CTA or to an end user, this may require a separate work package and project proposals.

The Work Package format presents the overview of the CTA/PEI effort for a three-year window.  Initially, it may be difficult to identify projects for Years X+1 and X+2.  As we achieve a better understanding of the long-range requirements of the Thrust Areas it will be easier to identify specific projects.   High, medium or low risk should be indicated for each project.

In most cases the proposal will be initiated by the CTA and PEI Leads.  In some circumstances ARL PET could push the project proposal to the CTA/PEI Lead.

Attachment 1 is used to describe the Work Package.  Upon completion and submission of t he project forms the PET lead will work with the CTA/PEI Leads to establish the Work Packages.  The format is shown here to promote understanding of the development of the program.

The information requested in Attachment 2, Project Form, does not differ substantially in terms of the information requirements previously provided for program years 1 and 2.  An explanation of the Project Form follows:

*  The Work Package Title is composed of the CTA/PEI and Thrust area names.  Ex., SIP-ATR.

*  The Point of Contact information is self-explanatory.

*  The Project Description spells out what work will be undertaken and the general results expected.

*  Contract Years Objective(s) is a more detailed examination of the results expected.

*  Contract Year Deliverables are an accounting of what will be provided for the benefit of the end user.

*  Customer/End Users is a straightforward statement identifying for whom are you doing the work.  Identify the end-user Point of Contact.

*  Benefit to the Warfighter documents the importance of the work to the end-goals of the HPC program and provides a means of quantifying the work to those outside of the MSRC.

*  Project Dependencies and Scope identifies those other CTA/PEI who will be contributing to this project and the scope of their contribution.   The CTA Leads will articulate how they will use the crosscutting technology teams to advance the CTA program.

*  Risk Element is the CTA Lead’s appraisal of the difficulty or uncertainty associated with the components of work.  This is expressed as a probability of achieving the results expected.  Optimally, the Work Package and its component projects contain varying elements of risk.

*  Required Funding Level is the CTA Lead’s statement of the funding required to pursue this project.  This does not include the costs incurred by other CTA/PEI who would identify the required funding level in their own project form for their contribution to this project.  Note that the funding level required for Year X is firm, and the funding levels required for Years X+1 and X+2 are estimates subject to revision as the program moves into those years.

The vision of the ARL MSRC is to serve as a leader and integral component of a DoD-wide, distributed computational technology and High Performance Computing and Communications environment.  Within this environment ARL PET will be on the leading edge.

WORK PACKAGE FORM

INSTITUTION_________________________________________        DATE PREPARED: ___________

WORK PACKAGE TITLE_______________________________

WORK PACKAGE DESCRIPTION

WORK PACKAGE OBJECTIVE

YEAR X Projects

1.

2.

…

n.

YEAR X+1 Projects

1.

2.

…

n.

YEAR X+2 Projects

1.

2.

…

n.

PROJECT FORM

INSTITUTION NAME:

WORK PACKAGE TITLE:

PROJECT TITLE:

POC NAME:

EMAIL:

PHONE:

FAX:

CTA or PEI:

PROJECT DESCRIPTION

PROJECT OBJECTIVE(S):

DELIVERABLES:

CUSTOMERS/END USERS:

BENEFIT TO THE WARFIGHTER:

PROJECT DEPENDENCIES AND SCOPE:

RISK ELEMENT:

REQUIRED FUNDING LEVEL:

Year X:

Year X+1:

Year X+2: