632-07 Proposal

to

# P. Norvig, Thrust Area Manager

Thinking Space Systems Thrust Area

Cross Enterprise Technology Development Program

## Prepared by:		_______________________________

Andrea Donnellan, Task Manager

(818) 354-4737

andrea.donnellan@jpl.nasa.gov

Approved by:		________________________________

Paul Stolorz, Manager

Division 39

Concurred by:		________________________________

Arthur J. Murphy, Manager

NASA Technology Program

### Jet Propulsion Laboratory

4800 Oak Grove Dr.

Pasadena, CA 91109

# Automated Data Analysis for Geodetic Sensor Networks
Proposal for 632-07

# Task Leaders

Andrea Donnellan, JPL, andrea.donnellan@jpl.nasa.gov, 818-354-4737

Jay Parker, JPL, jay.parker@jpl.nasa.gov, 818-354- 6790

John Rundle, U. Colorado at Boulder, JPL Distinguished Visiting Scientist, rundle@hopfield.colorado.edu, 303-492-5642

Geoffrey Fox, Northeast Parallel Architectures Center, Syracuse University, gcf@npac.syr.edu

# Product Description

NASA has identified the development of space-based and in situ sensor webs as a major technology requirement, especially by the Earth Science Enterprise. A crucial aspect of the development and deployment of sensor networks will be their ability to analyze data autonomously, so that  the deluge of information provided by these devices can provide scientific insight, not solely enormous volumes of data. We propose to use space-based geodetic data as a testing ground to develop a prototype software and pattern recognition infrastructure that will demonstrate the power of a wide-area network of data-collection assets when linked in a coordinated IT and analysis environment. This is a new, push task.

# Task Resources and Outline

|  | FY 2000 | FY 2001 | FY 2002 |
| --- | --- | --- | --- |
| Budget | $200K | $200K | $200K |
| Cost Sharing | * | ** | *** |
| JPL Employees | 1.0 | 1.0 | 1.0 |
| Contractors | $40K | $40K | $40K |
| TRL | 2 | 3 | 4 |

* 	FY99 $15K internal JPL funds from Space and Earth Sciences Program Directorate, anticipate additional funds in FY00.

**	FY01 - ESE/AIST? Up to $500K (White paper submitted to RFI with encouraging programmatic response).

***	FY02 - ESE/AIST; Expect additional $250 K from ESE geodynamics program.

# Benefits

NASA has recently committed a great deal of effort and funding to develop the means to observe and characterize the movements of the earth's crust that arise from plate tectonics leading to catastrophic earthquakes. Understanding the dynamic processes responsible for these events will require not only a national commitment to develop the necessary observational datasets, but also the technology required to use these data in the development of sophisticated, state-of-the-art numerical simulations and models. The models can then be used to develop an analytical and predictive understanding of these large and damaging events, thus moving beyond the current, more descriptive approaches now routinely employed. This will allow hypothesis testing and data integration on a scale not previously possible.

# Technical Approach

There are five major objectives to the proposed task.  1) We will develop pattern recognition and datamining software using earthquake fault interactions as a testbed.  2)  In order to do so we will develop the infrastructure to handle the heterogeneous large datasets and codes using an object broker oriented approach.  3) We will develop datamining algorithms for both large and sparse data sets.  The earthquake problem is ideal for this because we have large volumes of data that sample a short part of the earthquake cycle and are hence sparse in time.  4) We will address the NASA objective of developing predictive capabilities for natural hazards and, in particular, earthquakes.  5) We will produce general algorithms that are extensible to other sensor webs.  We have already begun talking with people involved in the Mars nav/comm constellation who are enthusiastic about our potential involvement in their program.

We will develop spatio-temporal pattern recognition methods that uncover the most important correlations in geodetic time series data. These feature extraction techniques, based on methods discussed in [1], that will ultimately enable autonomous monitoring systems that can flag important events and patterns in real-time for further decision-making. Simultaneously, we will develop and deploy an associated modeling and collaboration framework that will enable analysis of the data by a number of remotely collaborating participants and integration with large-scale computational models and other datasets such as InSAR. Although demonstrated initially on geodetic data, the product developed here will emphasize general methods, using open software standards such as XML, to ensure its applicability across a range of future sensor network systems in ground-based, earth orbiting, and deep space environments. The effort will use data from the Southern California Integrated GPS Network (SCIGN), a network of 250 GPS monitoring stations, seismicity data, and InSAR data. Since our approach gains enormous leverage from an existing sensor network resource, we are in a magnificent position to focus on the crucial software issues of managing and analyzing data and models across a large distributed sensor array, without incurring the large overhead of device construction and deployment. The lessons learned on this existing ‘testbed’ can then be transferred at very little cost during the design phase of future sensor webs.

# Status and Milestones

This is a new task.  However, the PIs have been involved in certain aspects of this technology for several years.  Donnellan is an expert in collecting, analyzing, and modeling geodetic data and has designed and deployed a network of autonomous GPS stations in the extreme environment of Antarctica [2–9]. Parker has experience in information technology, and electromagnetic modeling and has recently begun applying his expertise to earthquake related modeling problems [10–14]. Rundle has spent several years developing quasi-static dynamics codes of earthquake fault interactions and has recently begun applying pattern recognition to the problem of fault interactions and behavior [15–21].  Fox is at the forefront of the field of developing problem solving environments using object broker technologies and will enable the establishment of an infrastructure capable of handling the large volumes of data and complex models [21–27].

## FY 2000 Milestones:

-	Prototype time series algorithms implemented for a distributed array of geodetic sensors.

-	Data handling and modeling environment design completed.

## FY 2001 Milestones:

-	Integrated feature extraction/modeling and visualization scenarios implemented.

-	End-to-end prototype implemented for hypothesis evaluation/modeling/data integration.

## FY 2002 Milestones:

-	Testing and cross-comparison of space-based GPS, InSAR data and computational models completed.

-	Infrastructure deployed to demonstrate the scaling of autonomous data analysis/modeling to a 1000-node network such as PBO.

# Customer Relevance

Our product will provide immediate benefits to the Plate Boundary Observatory, a proposed follow-on to SCIGN consisting of over 1000 sites across the western US. Geodetic missions such as SRTM and LightSAR will provide unprecedented DEM’s over much of the world, which can also be incorporated into our framework (LightSAR will also provide valuable coseismic displacement fields and surface deformation information). More importantly, this work will point the way to an entire class of future sensor network applications for both the Space Science and Earth Science enterprises by developing a systematic approach to the testing of scientific hypotheses in a distributed sensor environment characterized by both large data volumes and large modeling requirements.

One of the six major questions in the NASA Administrator's strategic outlook asks how we can develop predictive natural disaster models. These events (e.g. volcanic eruptions) are potentially catastrophic if not flagged quickly and reliably. The datamining and pattern recognition software to be developed in this program will be directly applicable to early warning systems. Our approach is based on the development of general pattern recognition and datamining. We also address NASA's basic questions: "What cutting-edge technologies, processes, techniques, and engineering capabilities must we develop to enable our research agenda in the most productive, economical, and timely manner? How can we most effectively transfer the knowledge we gain from our research and discoveries to commercial ventures in the air, in space, and on Earth?"  By integrating these concepts within an object-oriented framework based on open standards, we can provide a blueprint for the design of fully autonomous continuously monitoring systems of heterogeneous assets that will underpin much of NASA/ESE’s needs in the future.

Not only will this product apply to solid earth science in the study of the behavior of earthquake fault systems, but it will also exploit data from the regional and global GPS networks for estimation of water vapor content in the atmosphere and total electron count in the ionosphere.  Members of this team already work closely with people in the above mentioned fields.  Results from these studies impact our ability to communicate during ionospheric storms, and allow the removal of noise due to water vapor from InSAR measurements.

The techniques developed here, then have direct application to the planned Mars nav/comm constellation (Mars network).  This sparse constellation of satellites around Mars will be used to support Mars navigation; studies of crustal deformation on Mars; nutation, rotation, and polar motion measurements, which yield information about the presence of a liquid core; and atmospheric studies.  The pattern recognition algorithms developed under this project will be crucial for navigation and datamining from this sparse Mars constellation.

# Technical References

[1] 	Rundle, Klein, Tiampo, and Gross, “Linear Pattern Dynamics in Nonlinear Threshold Systems,” Phys. Rev. E., manuscript submitted.

[2] 	Satellite Geodesy and Geodynamics Systems Group, GEM web page URL http://milhouse.jpl.nasa.gov/gem, GPS in Antarctica URL http://geodynamics.jpl.nasa.gov/antarctica

[3]	Lyzenga, G.A., W.R. Panero, A. Donnellan, The Influence of Anelastic Surface Layers on Postseismic Thrust Fault Deformation, J. Geophys. Res., submitted.

[4]	Argus, D., M.B. Heflin, A. Donnellan, F.H. Webb, D. Dong, K.J. Hurst, G.A. Lyzenga, M.M. Watkins, and J.F. Zumberge, Shortening and Thickening of Metropolitan Los Angeles Measured and Inferred Using Geodesy, Geology, in press.

[5]	Lundgren, P., M. Protti, A. Donnellan, M. Heflin, E. Hernandez, D. Jefferson, Seismic cycle and plate margin deformation in Costa Rica:  GPS observations 1994–1997, J. Geophys. Res., submitted.

[6] 	Donnellan, A. and G. A. Lyzenga, Fault afterslip and upper crustal relaxation following the Northridge earthquake, J. Geophys. Res., 103, 1998.

[7] 	Donnellan, A. and F.H. Webb, Geodetic observations of the M 5.1 January 29, 1994 Northridge aftershock, Geophys. Res. Lett., 25, 1998.

[8] 	Heflin, M.B., D. Dauger, D. Dong, A. Donnellan, K. Hurst, D. Jefferson, G. Lyzenga, M. Watkins, F. Webb, J. Zumberge, Rate change observed at JPLM after the Northridge earthquake, Geophys. Res. Lett., 25, 1998.

[9]	Cwik, T., C. Zuffada, D. Katz and J. Parker (1998),"Radar Scattering and Antenna Modeling on Scalable High-Performance Computers", in Industrial Strength Parallel Computing: Programming Massively Parallel Processing Systems, A. Koniges (ed.), Morgan-Kaufmann (in press).

[10]	Parker, J.W., "Accuracy of Wet Troposphere Radio Path  Delay Estimated from Infrared Emission," Optical Remote Sensing of  the Atmosphere: 1995 Tech. Digest  Ser., Vol. 2 , Opt. Soc. Am., 1995.

[11]	Parker, J.W., R. D. Ferraro, P. C. Liewer, "Comparing 3D Finite Element Formulations Modeling Scattering from a Conducting  Sphere," IEEE Trans. Magnetics 29, 1993.

[12]	Parker, J.W., T. Cwik, R. D. Ferraro, P. C. Liewer, P. Lyster, J. E.  Patterson, “Helmholtz Finite Elements Performance on Mark  III and Intel iPSC/860 Hypercubes,” The Sixth Distributed Memory  Computing Conference Proceedings, IEEE Computer Society Press, 1991.

[13]	Parker, J.W., and S. A. Bowhill, “Mesospheric KHI  Signatures in Reconstructed Broad-Band Rocket Probe Data,” J.  Geophys. Res. 96, 1991.

[14]	Rundle, Klein, Tiampo, and Gross, "Dynamics and Patterns in Earthquake Seismicity," AGU Book on Earthquake Physics, to be submitted.

[15]	Rundle, J.B., A physical model for earthquakes: 2. Application to southern California, J. Geophys. Res., 93, 1988.

[16]	Rundle, J.B., W. Klein, S. Gross, and D.L. Turcotte, Boltzmann fluctuations in numerical simulations of nonequilibrium threshold systems, Phys. Rev. Lett.,  75, 1995.

[17]	Yu, T.T., J.B. Rundle and J. Fernandez, Surface deformation due to a strike slip fault in an elastic-gravitational layer overlying a viscoelastic-gravitational half space, J. Geophys. Res., 101, 1996.

[18]	Kozuch, M.J., T.T. Yu and J.B. Rundle, Southeastern Caribbean sea level variability and viscoelastic relaxation, J. Geophys. Res., 101, 1996.

[19]	Rundle, J.B., W. Klein and S. Gross, Dynamics of a traveling density wave model for earthquakes, Phys. Rev. Lett.,  76, 1996.

[20]	Rundle, J.B., W. Klein and S. Gross, Physical basis for statistical patterns in complex earthquake populations: Models, predictions and tests, Pure Appl. Geophys., in press, 1999.

[21]	Northeast Parallel Architectures Center, Syracuse University, GEM web page URL http://www.npac.syr.edu/projects/gem/

[22]	Fox, G "Internetics: Technologies, Applications and Academic Fields" Invited Chapter in Book :Feynman and Computation", edited by A.J.G. Hey, Perseus Books, 1999.

[23]	Fox, G. C. "Approaches to Physical Optimization," in Proceedings of 5th SIAM Conference on Parallel Processes for Scientific Computation, Houston, TX, J. Dongarra, K. Kennedy, P. Messina, D. Sorensen, R. Voigt, editors, SIAM, 1992.

[24]	Fox G.C., Mills K., "InfoMall: an Innovative strategy for high-performance computing and communications application development", Internet Research, 4, 1994.

[25]	Fox, G.C.,Akarsu E., Furmanski W., Haupt T., "WebFlow -- High-level Programming environment and Visual Authoring Toolkit for High Performance Distributed Computing" in Proc. of SC98, 1998.

[26]	Fox, G.C., Johnson, M.A., Lyzenga, G.A., Otto, S.W., Salmon, J.K., Walker, D.W., Solving Problems on Concurrent Processors, Vol. 1, Prentice-Hall, Inc. 1988; Vol. 2, 1990.

[27]	Fox G.C., Furmanski W., "Computing on the Web,New Approaches to Parallel Processing,Petaop and Exaop Performance in the Year 2007 IEEE Internet Computing 1:2,38-46, 1997

# Letters of Support

June 21, 1999

Dr. Andrea Donnellan

Satellite Geodesy and Geodynamics Systems Group

Mail Stop 238-600

Jet Propulsion Laboratory

4800 Oak Grove Drive

Pasadena, CA  91109-8099

Dear Andrea,

As we have discussed, I am keenly interested in your CETDP Program Proposal: “Autonomous pattern recognition for sensor webs:  A prototype for space-based geodetic data”.  Let me know if there is anything the Southern California Earthquake Center can do to help facilitate your efforts in this regard.

Space-based and in-situ sensor webs are important in earthquake science and engineering, and the ability to analyze massive amounts of data from these webs efficiently, autonomously, and in real time is sure to lead to greater scientific insights than has been possible in the past through routine data reduction and analysis. In particular, the vast new seismic and geodetic networks, both contemplated and currently under construction, will lend themselves to the kinds of pattern recognition techniques you propose to develop. Ultimately, one of the real beneficiaries of this type of research might be the area of improved seismic hazard assessment and concomitant decision making.

To date, only a fraction of the information generated by seismic and space-based crustal deformation networks has been used for understanding the earthquake process. The spatio-temporal pattern recognition and other data mining techniques you are proposing have the potential to uncover aspects of the earthquake cycle not yet recognized.  The modeling and collaboration framework that are also part of your proposal should stimulate involvement by multiple groups of investigators, encourage multidisciplinary integration, and ensure wide applicability of your methodology.

In short, the technology you propose to develop will help pave the way for more fully exploiting sensor webs in many areas of earth and space science and engineering.  It is generally believed that future progress in many areas of science will require increased resolution, which translates into more observations in space and time.  In the earthquake business alone we are talking about factors of ten or more within the next decade!  This, in turn, will require innovative approaches and a new generation of data handling and analysis techniques if we are to fully exploit the vast amount of new information.  Your proposal directly addresses these needs.  I hope you will keep me informed regarding its progress.

Sincerely,

Thomas L. Henyey

Professor of Geological Sciences, University of Southern California, and Director, Southern California Earthquake Center

June 22, 1999

Dr. Andrea Donnellan

Satellite Geodesy and Geodynamics Systems Group

Mail Stop 238-600

Jet Propulsion Laboratory

4800 Oak Grove Drive

Pasadena, CA  91109-8099

Dear Andrea,

I am very interested in your CETDP Program Proposal: “Automated Data Analysis for Geodetic Sensor Networks.”  The geodynamics program within ESE has invested a tremendous amount into geodetic networks and techniques for studying earthquakes and volcanoes.  The product that you propose here directly addresses our need for efficiently analyzing the great wealth of data now being collected. The tools developed here can be used to develop an analytical and predictive understanding of large and damaging events from earthquakes and volcanoes, thus moving beyond the current, more descriptive approaches now routinely employed.   Your product will bring data collection and modeling efforts into a cohesive program within ESE’s Natural Hazards Program.

To fully mine the data from our missions within ESE, a seamless data handling/modeling/analysis environment must be established. Your product would result in numerous investigators utilizing solid earth data and models produced by NASA/ESE rather than a handful, and it potentially provides the outlet for millions of end users to explore the data. The cost per scientific output would drop dramatically, while concurrently loss of life and property will be mitigated through better models and hazard reponse.

Sincerely yours,

Clark R. Wilson

Program Scientist for Geodynamics and Geopotential Fields

Code YO

NASA Headquarters