## Sheet1
Date | Discription | GOV | Contractors | Compressed
2000-10-01 | Start of Ideal Year and on-going Discovery | x | x | 2001-06-01
2000-11-15 | SCXX | x | x | 2000-11-15
2001-02-01 | End of Discovery Process |  | x | 2001-02-01
2001-02-01 | Prepare White Papers (KTR) |  | x | 2001-02-01
2001-03-01 | HPCMP -- PRxx | x | x | 2001-03-01
2001-04-01 | White Papers to GOV | x | x | 2001-04-01
2001-04-01 | Selection Plan to GOV | x | x | 2001-04-01
2001-05-01 | Proposal Development and feedback |  | x | 2001-05-01
2001-06-15 | UGCXX | x | x | 2001-06-15
2001-06-15 | KTR Get Proposals and Review |  | x | 2001-06-15
2001-07-15 | Proposals to Government |  | x | 2001-07-15
2001-09-01 | Government ATP and feedback | x |  | 2001-09-01
2001-09-15 | Pet Review | x | x | 2001-09-15
2001-10-01 | End of Ideal Year and on-going Discovery | x | x | 2001-10-01

## Sheet2
Date | Discription | GOV | Contractors
2001-06-01 | Start of Compressed Year | x | x
2001-06-19 | Planning Meeting thru 6/21 | x | x
2001-02-01 | End of Discovery Process |  | x
2001-06-15 | UGCXX | x | x
2001-07-01 | KTR Get Proposals and Review |  | x
2001-08-01 | Proposals to Government |  | x
2001-07-18 | Planning Meeting thru 7/9 | x | x
2001-08-15 | NAVO Review 2 days | x | x
2001-08-21 | ASC Review 2 days | x | x
2001-09-15 | Government ATP and feedback | x
2001-10-01 | Start of Ideal Year and on-going Discovery | x | x