## Sheet1
ID | Task Name | Start Date | Finish Date | Percent Complete | Resources
13 | CDL-200: Enhanced Grid/Garnet Environment | Mon 10/1/01 | Mon 9/30/02 | 33% | Fox/Indiana U team
14 | Use and improve Garnet technology | Mon 1/28/02 | Mon 4/29/02 | 100% | Fox/Indiana U team
15 | Consult with CDLT team | Mon 1/28/02 | Mon 6/30/02 | 50% | Fox/Indiana U team | Change in CDLT Leadership
16 | Initial system available | Wed 5/1/02 | Fri 6/30/02 | 30% | U Team
17 | Establish Grid support for PET sites | Mon 9/2/02 | Mon 9/30/02 | 0% | Fox/Indiana U team | Need to review when CDLT Plans clearer
18 | Integrate into web service framework | Mon 4/1/02 | Mon 8/19/02 | 25% | U Team | Renamed Task
19 | Report on use and availability | Mon 8/19/02 | Mon 8/19/02 | 0% | Fox/Indiana U team
20 | Use to support scientific research | Mon 8/19/02 | Mon 9/30/02 | 0% | U Team
21 | Final report | Mon 9/30/02 | Mon 9/30/02 | 0% | Fox/Indiana U team