# NPAC Transition Plan

It is appropriate to set up a process to cover the next few months to ensure that

- We address as well as possible the deliverables expected by our sponsors

We enable a smooth transition from the current team to the group who will continue the activity at FSU.

We will assume that the situation will continue more or less as is to early in Y2K but after that, we can expect

- Some of NPAC’s infrastructure will suffer as staff will gradually leave

- Some federal funding will be withdrawn from NPAC and either lost or transferred to FSU.

Hmm… I understand the idea of funding transfer, but why should funding be withdrawn from NPAC and lost? This seems a waste, doesn't it?

- The new team at FSU will consist of a subset of those currently here and a few new people – perhaps already at FSU.

- NPAC will only have “skeleton capabilities” starting around May 1,Y2K

- WebWisdom.com and Translet will increase their role and it is necessary to cleanly separate intellectual property between Syracuse University and commercial ownership.

I rather see a problem with separating between intellectual property of SU and FSU. As WebWisdom.com enjoys full and vigorous support of Syracuse University, the problem of WW.com/SU separation does not seem to be of much significance. Given your resignation, SU perceives WW.com as a technical continuator of the collaboration and distance learning technologies and expects to use this expertise in new federal contracts currently under development.

Ben mentioned your concerns regarding your ability to use the code for which WW.com has license rights in your further research. I personally do not see this as a big problem, as long as any transfer of the code outside federal agencies and your group at FSU is consulted and agreed upon with WW.com. We should just talk about it.

Changes are needed in principle for all NPAC activities but are immediately relevant for “core Tango” and “Tango applications/Portal Services”, as McCracken and Podgorny will not come to FSU.

Given this preamble, I am changing NPAC’s organization. There will be a new activity – termed “NPAC Transition Project”, which will be led by David Bernholdt. This project will be responsible for ensuring completion of deliverables expected by our sponsors and that this work will smoothly transition to the group who will continue the activity at FSU. Some of the Individuals now reporting to McCracken and Podgorny will instead report to Bernholdt. McCracken and Podgorny will act in a technical advisory role to this Transition Project.

I have no problem with working with Dave. I'm not sure however, what the effective change is going to be. There are plans, and there is practice. Please, see my comment below.

As some of the Tango team will soon transfer to WebWisdom.com activities led by Podgorny, the first step is for Bernholdt to meet with those involved to plan on

- Implementation plan for deliverables and how that impacts next semester’s classes

I don't see any reason other than total lack of financial support that any of this should be affected at all. I have sufficient authority among the troops to ensure that PET project deliverables are met, and that the classes get necessary technical support.

- Which  (or which fraction of salary for) staff and students are to be funded out of NPAC’s current funding and which out of commercial sources

I uphold my part of the deal. Starting January, I will provide an equivalent of 65% (approx. 2/3) of  monies needed to pay current salaries and fringe benefits of the 8 individuals in my group (L.Beca, G.Lewandowski, K.Olszewski, T.Major, P.Roman,  R.Trzaska, T.Stachowiak, and B. Winnowicz). This is covered by a contract I have in place and which I expect to have signed by end of the next week. I might be able to also support a student or two, but this is not certain yet - I'm working on additional source of money. This is as much as I can contribute for now. I'm working with CASE on a overhead-free mechanism to direct this money to an SU account.

If the VC effort bears fruits, or if more contracts and sales are realized, this amount can be increased, although beyond certain limit this seems to work against the idea of transition: shall the entire group disappear shortly, PET deliverables and other elements of the transition could be seriously handicapped.

How this money is going to be used is a difficult technical issue. As the contract I have requires intense effort of WW.com, I cannot agree that NPAC picks and chooses best individuals at will. This is the point when Dave's role becomes critical: he should be a guardian of NPAC interest, so that NPAC gets proportional chunk of quality time of all troops, as dictated by fractional funding. I agree that such supervision is necessary and it takes the burden of conflict of interest from me. Technically, I don't think that this can be planned for more than few weeks in advance, so my proposal is that I should work with Dave on the daily basis, monitoring progress and project needs, and coordinating the efforts on the short-term, flexible basis. I'm confident this can be arranged and executed, as Dave and me have a history of very good cooperation. This is what I perceive as a central issue to get the results you desire. How do you want to set up who reports to whom under such circumstances: I have no clue. In general, I believe  that in  situations as complex as the one we deal with, only honest cooperation can get the job done, not the administrative enforcement. I declare my support for the idea and will do my best to satisfy all project requirements. If, as you say, some funding may disappear, this should not be due to inferior performance.

Of course, I will gladly relinquish responsibility and supervisory role for people with self-contained and marginal projects, such as Jin's SciVis, Jake's work etc.

I think we should start from SoW and an inventory of things done and outstanding, draw a summary SoW, and get things started.

I want to be very clear that this is a procedural change intended to shorten the chain of command for sponsored activities (especially PET) and make it easier for Marek and Nancy to transition to new roles within the university or associated companies when the time is right, with fewer worries and possible conflicts of interest.  I deeply appreciate the work that they and their groups have done for NPAC over the  my hope with this change is to make the transition as straightforward and uncontroversial as possible for those choosing to remain in Syracuse as well as those moving to Florida.