PROPOSAL ABSTRACT

Section I. Administrative

(1) BAA number:  BAA 97-09

(2) Technical topic areas: "Tools for Sharing Views and 
                                           Prototyping and Evaluating Collaborative Applications"

(3) Proposal title: “Development and Evaluation of Tools for Web Technology Based Collaboration and Visualization in Command and Control, Health Care and Training”

(4) Technical point of contact:

Prof. Geoffrey C. Fox

Director Of the Northeast Parallel Architectures Center

Professor of Computer Science and Physics

111 College Place

Syracuse, New York 13244-4100, USA

Tel.: 315-443-2163, Fax: 315-443-1973

http://www.npac.syr.edu Email: gcf@npac.syr.edu

(5) Administrative point of contact:

Matthew E. Clark

Office of Sponsored Programs

113 Bowne Hall

Syracuse NY 13244-4100

Tel: 315-443-9356, Fax: 315-443-9361

Email: clarkme@syr.edu

- Summary:

We  will establish the critical features and performance needed in future Web based collaborative environments by assessing prototypes in three significant application areas – Command and Control, Healthcare and Education. These will be implemented in terms of an existing leading edge Web based collaborative system TANGOsim built as part of a Rome Laboratory project CIV. The base capabilities of TANGOsim are one to two years ahead of competitive systems and are being used in a significant C2 application demonstration. TANGOsim already has two key novel features. Firstly it is linked to a Web hosted Oracle database where it can log all transactions of the collaborative sessions and which can be used in asynchronous collaboration as well as our assessment task. Secondly it has generalized the typical session manager of collaborative environments to a full function event driven simulator. This allows TANGOsim to support collaborative linkage of heterogeneous sessions with different views of the same base object. Further it allows one to use both virtual (scripted) and real collaborators which greatly enhances both the assessment process and training for all applications.

The project is led by NPAC at Syracuse University which designed and built TANGOsim with PI Geoffrey Fox; the C2 application is the responsibility of the Vanguard Research Inc.; Healthcare applications will be built by a team from John Hopkins Medical School led by Joel Saltz who has a joint appointment with the Computer Science department at Maryland which will be involved in assessment task. The requested budget is $950K per year for three years. Cost sharing includes use of  education applications of TANGOsim being developed by NPAC to support distance education, which will be included in assessment task. Deliverables include enhancements to TANGOsim to support scalable large scale collaboration, multimedia annotation, mobile users and immersive environments. Several different applications in the three areas will be developed in terms of TANGOsim and their use will be analyzed in terms of requirements for  performance and functionality of the various multi-use services available in TANGOsim.

(7) Contractor's type of business: "Other Educational"

Section II. Detailed Proposal Information

A. Innovative claims of the proposed research

B and D. Deliverables and description of the results

- Use of leading edge Web Technologies to enhance a Java Collaborative framework TANGOsim to support multiple complex heterogeneous applications in both synchronous and asynchronous modes

- Enhancement of current central server model to a distributed cooperating mode using most appropriate of emerging Java server technologies and JDBC distributed database

- Allow Web or traditional(C++) applications to be conveniently integrated with TANGOsim and to interact with each other through customizable filters. Support tools to conveniently debug new applications in collaborative mode

- Allow both real and virtual users of the system with a general Discrete Event Simulation capability integrated into TANGOsim control engine. Support pause and playback of session and real time modification of simulation script

- Tools to support performance measurement in terms of measurement primitives (based on Pablo SDDF developed at Illinois) built into applications and logged by an attached Web Hosted database

- Services provided by Tango will include 2D and 3D stereo Geographical Information Systems, digital audio images and video with adaptive codecs and database indexing, real time annotation and review of multi-media sessions, session management, shared information resources such as white boards, web pages etc.

- Immersive Environment based emerging web (VRML2) standards and optimized for  high performance

- C2 Applications involving over 10 active participants which can be real or virtual and 100’s of questioners

- Healthcare applications including training of residents with experts and observers and team health care with synchronous and asynchronous interaction. Tools to support summary of multimedia records for later expert consultants

- Educational applications including University and K-12 distance teaching of computer science and physics with up to 100 active students and low speed links addressed by local caching of course material

- Tools for evaluation of collaborative sessions logged in database in terms of linked Java visualization applets and statistical analysis libraries.

- Summarize results of applications in terms of architectures of TANGOsim, choices in its integration technology, performance and functionality of basic services (generic applications) and needed compute and network resource.

F. Cost, schedule, and milestones

Budget:                                                  Year 1          Year 2          Year 3

Task 1)Enhance and support                  $350K         $250K         $200K

TANGOsim and associated services

Task 2)C2 Applications                         $225K          $225K         $150K

Task 3)Health Care Applications           $150K          $150K         $100K

Task 4)Distance Education Application   $0K              $0K             $0K

Task 5)Evaluation                                  $100K          $200K         $325K

Task 6)Integration, Administration        $125K          $125K         $175K

and Demonstrations

Total                                                       $950K         $950K          $950K

Task 1: Enhance and support TANGOsim and associated services

Year 1: Evaluate TANGOsim in terms of application requirements and other collaborative systems. Initial Enhancements (multimedia annotation, assessment tools)

Year 2: Continuing Enhancements (mobile users, scalable service)

Year 3: Continuing Enhancements (immersive environments)

Tasks 2-4)Applications

Year 1: Find requirements and generate initial design of applications in each of 3 areas. Develop first prototype implementations.

Year 2: Complete major applications to be used in assessment process

Year 3: Continue to improve and extend applications

Task 5: Evaluation and Performance Measurement

Year 1: Design evaluation and performance measurement process and initial TANGOsim support tools

Year 2: Initial evaluation of prototype applications – feed lessons into TANGOsim tools and evaluation process

Year 3: Complete analysis of final applications with evaluation of lessons for collaborative systems

Task 6: Integration, Administration, and Demonstrations

Years 1-3: Semi-annual major demonstrations of selected applications. Integrate applications in terms of common service needs. Reporting and coordination of subcontractors.

G. Technical rationale; Technical approach and Implementation Plan

H. Comparison with other ongoing research

I. List of key personnel and concise summary of their qualifications.

1. Geoffrey Charles Fox.

Fox is Director of NPAC and Professor of Computer Science and Physics and an internationally recognized expert in the use of parallel architectures and the development of concurrent algorithms. He led a major project to develop first prototype high performance Fortran (Fortran90D) compilers with language independent runtime.  He has always emphasized the role of applications in driving and validating technology. This is illustrated by his recent book "Parallel Computing Works" which describes the use of HPCC technologies in 50 significant application examples.  Fox directs InfoMall, which is focused on accelerating the introduction of high speed communications and parallel computing into New York State industry and developing the corresponding software and systems industry. Much of this activity is centered on NYNET with ISDN and ATM connectivity throughout the state including schools where Fox is leading developments of new K-12 applications that exploit Web technology. With Rome Laboratory, NPAC has developed a Web based command and control application indicating how this COTS technology can be effectively used in DoD applications.

2. Joel Saltz 
Joel Saltz is Associate Professor of Computer Science at the University of Maryland, College Park, and Associate Professor of Pathology at Johns Hopkins Medical School. He is director of the High Performance Systems Software Laboratory, and of the Center for Computer Science in Medicine. Saltz leads a research group that is dedicated to developing applications driven systems software. He has published over 100 papers in a variety of areas in systems software including tools and compilers for distributed and parallel machines, databases, and the use of performance monitoring and program migration to optimize performance of distributed Internet based programs. His applications work includes the development of performance optimization and ontology generation methods to facilitate medical database interoperability. He is also developing Web based software to support multimedia computerized medical records along with software to support clinical conferencing.

J. Discussion of proposer’s previous accomplishments and work

Section III. Additional information

References