## Sheet1
MBC 635 - homework #1
Problem 3 on page 272
Tomasz Stachowiak
k1 = | 30
r = | 0.9 | 90%
b = | -0.152
|  |  |  | Cumulative | Hours | Hours | Total
|  |  | Conversion | hours | needed | available | hours
Week | Units | Cumulative | factors | needed | per week |  | available
1 | 20 | 20 | 0.73039 | 438.234 | 438.23 | 1600
2 | 65 | 85 | 0.62043 | 1582.0965 | 1143.8625 | 3200
3 | 100 | 185 | 0.56069 | 3111.8295 | 1529.733 | 4800
4 | 140 | 325 | 0.50586 | 4932.135 | 1820.3055 | 6400
5 | 120 | 445 | 0.50586 | 6753.231 | 1821.096 | 8000 | 7000
Solution is not feasible since amount of hours needed in weeks 4 and 5 is higher than
amount of hours available for the week. However, since the amount of cumulative
hours needed for the whole process (445 units - 6754 hours) is lower than the limit (7000 hours)
process can be improved by scheduling numberof units produced differently
(e.g. as shown on the Table 2)
|  |  |  | Cumulative | Hours | Hours | Total
|  |  | Conversion | hours | needed | available | hours
Week | Units | Cumulative | factors | needed | per week |  | available
1 | 75 | 75 | 0.62043 | 1395.9675 | 1395.9675 | 1600
2 | 85 | 160 | 0.56069 | 2691.312 | 1295.3445 | 3200
3 | 80 | 240 | 0.56069 | 4036.968 | 1345.656 | 4800
4 | 112 | 352 | 0.50586 | 5341.8816 | 1304.9136 | 6400
5 | 93 | 445 | 0.50586 | 6753.231 | 1411.3494 | 8000 | 7000
New solution should not introduce any additional costs since total
weeks needed for the operation is the same. Moreover, we can reduce it,
assigning less workers (1411/40 = 36) to the process.
Comment: Conversion factors were not available for all the unit values. Therefore, I took
the closest possible value that did not exceed the given value.
This way analysis was more conservative and results guarantee feasibility of the operation
Although, solution could be probably improved even more with exact data.