# RIMPAC 2000: Exercise “Strong Angel”

Eric Rasmussen, MD, FACP

## Third Fleet Surgeon

619-524-9541 shipboard

619-925-7701 cellular

Eric.Rasmussen@coe-dmha.org

20 November 99

Post-MPC

Recognizing that this is a first effort and everything will be hard, our goal in this exercise will be an effective legacy for those who will do this next time.

- Overview:

  - During a period of escalating tensions between two island nations, the United Nations requests a Coalition Task Force to serve as a calming presence in the waters off the most affected of the islands. On that island are two countries, Green (the good guys) and Orange (not the good guys). Ethnically Green citizens of Orange (read: Kosovar Albanians) are subjected to persecution and flee across the border into Green. The influx worries Green, which requests assistance in the management of the refugees. The UN Secretariat agrees, and a civil-military operation is initiated that has UN agencies establishing a refugee camp in Green. Those agencies (UN High Commissioner for Refugees (UNHCR), World Food Programme (WFP), UNICEF), guided by the Office of the Coordinator for Humanitarian Assistance (OCHA), are to be supported in any fashion they deem desirable by elements of the Coalition military. Essentially, the camp will be a military effort, overseen by the UN agencies who know how to do it.

  - The camp will be established on the northwest corner of the Big Island of Hawaii. The site, called Puu Paa, is below an 800-foot hill, facing down slope across very rough lava scrublands to the ocean visible about 12 miles away. There will be two sites, the refugee camp itself and a Civil-Military Operations Center (CMOC) area. There will be roughly 60 five-person Red Cross tents within the camp, with a few larger tents for various support functions including meals, showers, recreation, admin, and storage. The CMOC section will contain more storage, communication links, staff housing, experimentation, and various public relations areas for visitors.

  - We will support roughly 300 live volunteers for about five days in the camp. The volunteers will be of mixed ages, 15 to 65,  and genders, and they will be selected for their suitability to the rigors of several days in a potentially harsh environment. We recognize that there is nothing in the area. There is no power, water, food, or shelter. All facilities must be developed from scratch. Fortunately, the camp will be less than six miles from a small city with excellent medical facilities, and the site surveys have been somewhat reassuring. The safety of the civilian volunteers will be paramount.

  - The material for the camp (tents, cots, kitchens, etc) will be loaded on an amphibious ship (probably the USS Boxer) and transported from Oahu to the landing area at K-docks on the Big Island. The Marines will transport by truck from there and establish the camp to UNHCR specifications on the 9th and 10th of June. The breakdown of the camp will be done on the 15th and 16th of June, with material returned to it’s site of origin on Oahu as required. We recognize that the supporting Marines will retain some of the material on the island for ongoing exercises.

  - There will be an extensive experimental component to Strong Angel. One section in the CMOC area will be dedicated to the trials of information management in an austere environment. The experiments run the gamut from high-bandwidth informatics support, to the interviewing of refugees for war-crimes documentation using digital transcription, to solar powered computer systems.

  - There is a special effort to understand chemical and biological response capabilities for information management. A sub-exercise, called Sea Breeze (for CBRE, Chemical-Biological-Radiological-Envirotoxic) will stimulate the requirements that will test the primary experimental effort, a DARPA project called TIDES. TIDES is an acronym for Trans-lingual Information Detection, Extraction, and Summarization. It is a web portal to resources not previously available, and will have its initial test in our attempt to ferret out the circumstances surrounding a Sudan-like event.

    - Background: On 23 July 99, rumors surfaced that a chemical agent may have been used in Sudan against a civilian population. Evaluating that report proved challenging, so the TIDES portal under development has been adapted to look at a similar question in this exercise.

    - In addition, we will have a malignant contamination of a water source within the camp by Orange insurgents masquerading as refugees. Our response to that will be designed to assess information management tools with particular attention to epidemiology in refugee camps, and the appropriate response.

    - NOTE: We will NOT be managing a chem-bio casualty problem. These experiments are to test information management tools. There will be no release, no casualties, no moulage, no MOPP gear, no decontamination procedures, and no general alerts to the refugees. It is more than a CPX,  but Sea Breeze has a quantifiable experimental component to it as well.

- Any questions regarding any facet of the exercise can be directed to the Officer Conducting the Exercise (OCE), LCDR Eric Rasmussen, Medical Corps, USN, the Fleet Surgeon for Third Fleet. Contact details are at the head of this paper.

- Dates

  - 06 June: Coronado sails to BI from PH, Boxer arrives in PH same day

  - 07 June: Coronado off BI, Boxer onloading Oahu, and Site Team ashore

  - 08 June: Coronado offshore, Boxer sails for BI

  - 09 June: Coronado offshore, Boxer offloads K-docks, construction begins

  - 10 June: Refugees begin late arrival, Coronado and Boxer sail to PH

  - 10-15 June: Refugees present, repatriated afternoon of the 15th

  - 14 June: Coronado sails from PH to BI

  - 14-16 June: Coronado offshore

  - 16 June: Coronado departs for PH, Camp breakdown.

  - 19 June: Hotwash on Coronado, in port in Pearl Harbor.

- Physical construction

  - There are two exercise sites, roughly two miles apart, linked by an unpaved road.

    - Landmark: Wiamea-Kohala Airport

      - Two miles south of the town of Wiamea on Hwy 190, the Hawaii Belt Road.

      - Single runway, 5197 feet x 100 feet, paved asphalt. Commercial. Not normally manned.

    - Civil-Military Operations Center site

      - The Wiamea-Kohala airport is on the left (east)  side of  Hwy 190, the road coming from Wiamea. The CMOC area will be located just off that same Hwy 190. The access gate for the dirt road leading to the CMOC site and the refugee camp is roughly 400 yards south of the airport entrance on the right (west) side of the road when going south. The gate is locked and is controlled by Parker Ranch.

      - The CMOC site is located inside a second access gate, roughly 200 yards from the paved Hwy 190, on the north side of the dirt road, closer to the airport to minimize communication distances. The area is open, so the precise siting of the tents will be at the discretion of the assigned teams.

      - The CMOC site will include tents, with power and light, for:

        - a CMOC

        - for experimentation (TIDES and the ECU bridge)

        - for staff living quarters for 20 outside of the organic CSSG Marine staff

        - for the Coalition Information Bureau

        - a kitchen

        - a dining facility

        - bulk commodities

        - There will be portable latrines on-site

        - There will be a shower unit on-site.

    - Refugee camp site

      - The refugees will be located on the west side of the Puu, sheltered in a forest of dead trees and facing the water. The site is roughly two miles from Hwy 190 on a dirt road curving south around Puu Paa. There is only the single access road from Hwy 190 in past the CMOC site on the right and continuing on to the refugee camp.

        - 019.59.11.6  North

        - 155.42.15.2  West

        - 3400’ altitude

      - The refugee camp will be surveyed and constructed by Combat Service Support Group-3 (CSSG-3), US Marine Corps. The survey and construction will be to standards set by the United Nations High Commissioner for Refugees (UNHCR), and will take place in concert with UNHCR staff on site.

      - The camp will be open. There will be no enclosing barrier, and there will be no impediment to movement beyond simple safety.

      - CSSG will also manage the camp for sustainment, again in concert with United Nations agencies skilled in the subject areas.

        - World Food Programme for nutrition and bulk commodity management

        - UNICEF for the care and safety of those under age 18

        - UNHCR for the sustainment of refugee actors to standards set by the UNHCR and the International Committee of the Red Cross (ICRC)

      - The refugee camp site will contain tents, with power and light, for:

        - 300 people (roughly sixty 5-person Red Cross tents)

          - no power or light required in the Red Cross tents

        - a shower unit

        - an organic Marine Medical unit

        - portable latrines

        - kitchen

        - dining facility

        - recreation

        - administration

        - bulk commodities

        - Marine CSSG staff housing

- Requirements:

  - Road grading x1 on the 4WD access road in late May

  - Water and water storage for 350 people for 7 days, two sites

  - Meals (Tray-pack 3x/day) for 350 people x 7 days, two sites

  - Portable latrines for 350 for 7 days, two sites

  - Laundry and shower services for 350 for 7 days, two sites

  - Force protection

  - Media support

  - Experiment support

- Scenario sequence detail

  - Coalition arrival includes a CMOC structure afloat since ethnic persecution is recognized and intervention seems likely.

  - Area of probable refugee migration is inaccessible. Negotiations bring a hesitation to the developing problem.

  - Escalating tensions, refugees recognized in Green, Green asks UN for help.

  - Significant Green infrastructure damage inhibits air transportation to the Green capital at Hilo.

  - Local US Ambassador discusses it with Green, then the Ambassador requests, through State, Coalition assistance with security, communications, and logistics support to a humanitarian operation. UNSC says Coalition help authorized and appreciated. State notifies SecDef, then CINCPAC, then Coalition JTF Commander.

  - Through concurrent efforts behind the scenes, the CJTF Commander has identified assets to the Theater CINC.

  - UNSC tasks OCHA to coordinate. OCHA designates UNHCR lead, contacts are made, and civ-mil coordination begins at the Field level. An afloat CMOC desired initially since staff endangerment is likely during the coordination and assessment phase.

  - UN staff brought to Coronado for development of an afloat CMOC.

  - An assessment team is sent ashore by helo. Site selection is done from the air by a Joint Assessment Mission (Mil G4, Mil Security (2), OCHA, DART (2), WFP, UNHCR, UNICEF) from the Coalition.

  - A list of requirements is generated afloat through a GroupSystems session in the CMOC. Those requirements are passed to military log / comms / security.

  - Implementing partners delegated, military fills the gaps:

    - Comms

    - Sustainment

      - Sanitation, food, water, shelter, security

    - Bulk commodity movement

    - Registration and documentation

    - Medical

  - Movement of goods and supplies already underway is refined based on the discussions within the CMOC. Sea-Based logistics through Boxer onload at K-bay, Oahu.

  - Transition CMOC from afloat to ashore once the camp site can sustain adequate civ-mil communications.

  - Begin receiving refugees once a bare infrastructure is present.

- Requested from CSSG-3 for CMOC and Refugee Camp (RC) areas

  - Tents:

    - Eighteen GP – Medium ( 12 CMOC + 6 RC)

      - RC (6):

        - Medical

        - Recreation (2)

        - Admin

        - Bulk commodity (2)

      - CMOC

        - CMOC (2)

        - Staff Housing (2)

        - Experimentation

        - Joint Information Center

        - Joint Visitors Bureau

        - Press housing

        - Bulk Commodity (4)

      - (contingency plan for housing 300 people if there are real-world requirements for IFRC tents)

  - Latrines, portable:

    - Eighteen  (6 CMOC + 12  RC)

  - Meals:

    - 7500 (350 people x 3 meals/day x 7 days)

    - Tray-Pac – MRE - Tray-Pac

  - Water

    - 350 people x 7 days (sustenance + hygiene)

      - drinking

      - cooking

      - shower (CMOC area and Refugee area separated)

      - laundry (optional)

  - Vehicles:

    - Four bulk transport trucks from 09-18 June

    - Three buses on 10 June pm

    - Five buses on 11 June all day

    - 7 buses on 16 June all day

    - Three Ready vehicles (high-occupancy 4WD) for general transport 09-17 June

    - Three Six-Cons for water (CSSG refinement with WFP)

    - Road grader for access road on 05-06 June

  - Cots: 350

  - Blankets: 500

  - Tables, folding: 40

  - Chairs, folding: 100

  - Power/Light modules for tent interior illumination: all tents except Red Cross housing.

  - Area lights:

    - refugee area security

    - CMOC area security

  - Electrical power:

    - Non-lighting power to all non-housing tents.

  - Security detachment:

    - Camp area security

    - CMOC area security

    - VIP/Press escort

      - All areas are unfenced

      - Security is for the protection of the camp, not incarceration. All inhabitants are free to leave at any point and for any reason. We will provide transportation to their embarkation point at their request.

  - Medical

    - Real-world contingency (minor management and major stabilization)

    - Use organic CSSG-3 Medical

      - Competent hospital roughly four miles distant

      - EMS response roughly 15 minutes

      - Air response roughly 4 minutes flight time.

      - Radio links to be established early and tested twice daily from RC and CMOC.

  - Manning of CSSG-3 at Third Fleet

    - Provide Senior LNO to Strong Angel beginning at arrival of USS Coronado in Pearl Harbor in late May 2000.

- Health services (screen, baseline, emergency care, routine care, surveillance, vaccinations)

  - Medical support from CSSG-3

  - Link with Fire and Rescue

    - Ensure radio contact

    - Grade road for ambulance access

    - Get precise coordinates for Air-Evac

  - Get forms for UN landmine injury reporting

  - Get refugee medical reporting forms

  - Get CENTAUR installed for real-world casualties

- Recreation

  - IFRC

  - Games

  - Disney

  - Frisbees

  - Dances

  - Stories

  - Astronomy lectures

  - Geology lectures

  - Concerts

- Media collaboration

  - PAO

    - Reuters

    - Discovery Channel

    - UP/AP

    - Navy Times

    - Disney ABC

    - CNN

    - NPR

- Participants

  - US Military

    - Navy (C3F)

    - USMC (CSSG-3)

    - TRANSCOM

    - Air National Guard

    - Army

    - Naval Postgraduate School

  - International Organizations

    - IFRC (American Red Cross)

    - CARE

  - UN Agencies

    - OCHA (now in East Timor)

    - UNHCR (currently operating in 40 countries)

    - WFP (currently operating in 80 countries)

    - UNICEF (currently operating in 130 countries)

  - Foreign military

    - US

    - Australia

    - Canada

  - Civilian refugee actors

    - Age 18 to 65

    - Both sexes

      - Univ of Hawaii - Hilo

      - COE

      - Tripler AMC

      - Boy Scouts

      - Girl Scouts

      - Navy Reserve (CBRE, camp security problem)

      - Sea Cadets

      - Explorers

      - Unrestricted volunteers

    - Medical screening

    - Liability Release form

    - Liability Release lecture

    - Safety brief

    - Genuine registration to UNHCR-IOM standards

  - COE

    - Ashore and afloat

- Communication

  - COMM PLAN frequency allocations (Six total)

  - HF: 3

    - Two HF voice, (MED-1, MED-2) opposite ends of the HF spectrum

      - One HF data (MED-Data)

      - HF voice and data stations with SelCall

      - CODAN 9360 (or NGT)

      - CODAN 9002 modem

        - Both shipboard in JLCC

  - VHF: 5

    - Three VHF voice (Camp1, CMOC Command,  UN-Net)

      - Two VHF data: (CMOC Data-1, CMOC Data-2)

    - VHF personal hand-held (10)

    - VHF repeater

      - On Puu Paa

  - Cellular

    - RIMS email pagers

      - Transceiver on Puu Paa

  - IP addresses

    - In the CMOC spaces

      - just one on the Master Server afloat on Coronado. Use the HF radios

      - Use the JLCC with the Sun Q-70 and the SBBL/J-9 server.

    - On the beach: wireless IP

      - One address

- Shipboard coordination for personnel logistics, berthing, and messing

  - WFP (3 total)

    - 1 (one) O-5 equivalent staff from 04-19 June)

    - 2 Staff passing through to the camp (04-09 June)

  - UNHCR (5 total)

    - 4 passing through to the camp (June 04-09)

    - 1 staying afloat (04-19 June)

  - OCHA

    - 1 afloat from 04-19 June

  - UNICEF

    - 1 afloat from 04-19 June, 2 from 04-09 June

  - COE

    - 2 afloat from 04-19 June

  - CMI

    - 3 afloat from San Diego

  - DARPA/MITRE

    - 1 O-4 equivalent from San Diego

  - Army Civ-Mil

    - 1 O-4 from First Corps from 04-19 June

  - Air Force

    - 1 O-6 from 04-09 June

  - Marines

    - 2 O-4 from 04-19 June

  - Combat Camera

    - Two from 04-19 June

  - Naval Postgraduate School

    - One civilian GS-15 (04-19 June)

- TRANSCOM support

  - 1 metric ton from Kampala (Entebbe) to Pearl Harbor on 06 June.

    - Requested for pursuit by Chief of Staff, C3F

  - Air backload on 18 June from BI to Oahu

- Agency POCs

  - Third Fleet Exercise Coordinator

    - LCDR Eric Rasmussen, MC, USN

      - 619-524-9541 afloat

      - 619-925-7701 cell

      - Eric.Rasmussen@coe-dmha.org

  - Third Fleet JAG

    - CDR Steve Rodgers, JAG, USN

  - Center of Excellence in Disaster management and Humanitarian Assistance

    - Mr. Jim Rogers

      - 808-296-1205 cell

      - Jim.Rogers@coe-dmha.org

  - III MEF

    - Third FSSG

      - CSSG-3

        - 1LT Lee

  - Parker Ranch

    - Steve Troute

  - CINCPACFLT Real Estate Office

  - UN Agencies for participants

    - UNSC

    - OCHA

    - UNHCR

    - WFP

    - UNICEF

  - American Red Cross

    - Hawaii

  - RIMPAC Coordinator, Third Fleet

    - LCDR Adam Mroz, RAN

  - K-docks on the Big Island

    - USMC through Steve Troute at PTA

  - University of Hawaii for students

    - Dr. Michael Ego

Further considerations:

- Test the experimental technologies:

- Sponsor, Subject

- POC, Analyst

- DARPA: TIDES Portal

  - POC: Andy Merlino, review by Lee Kollmorgen

- DARPA: Lincoln Labs Two-Way translation

  - POC: Cliff Weinstein, review by Lee Kollmorgen

- DARPA: One-Way Translation for refugee interviews

  - POC: Ace Sarich and Marine Acoustics, review by Lee Kollmorgen

- DARPA: Interactive Drama - WMD

  - POC: Lee Kollmorgen, review by COL Annie Sobel

- DARPA: Joint Logistics Collaboration Center

  - POC: Eric Rasmussen and Bran Ferren, review by Mark Adkins

- ECU: Telemedicine Practice Suite and Bridge

  - POC: David Balch, review by Dave Warner

- COE: CENTAUR Information Management

  - POC: Enzo Bolletino, review by COL Annie Sobel

- SSC: Strong Angel documentation

  - POC: Gerard Gibbons, review by Bob Younger

- C3F: RIMS email paging system

  - POC: Mike Hopmeier, review by NPS

- C3F: Solar power for austere infrastructure

  - POC: Eric Rasmussen, review by NPS

+++++++++++++++++++++++++++++++++++++++++++++++++++++++++++++++++++++++++

END