# ADMINISTRATOR:

## Goals - What goals do you want to meet, curriculum, skills, etc.

## Vehicle - What project will accomplish the goals?  Curriculum focus.

## Technology Vehicle - What Internet, e-mail, telephone, snail mail, etc. technologies will be used / required?

## Required Skills - What computer knowledge do I need to have?  Can I do it?

## Post - Advertise the idea by BBS or mailing list.

## Project Page - Create an information page about the project.

## Sign up - Create a sign up page.

## Organize - Organize the people, e.g. grad level, computer  experience, language, etc.

## Establish Partners - Partner the schools.  May take multiple tries.

### Trouble shoot why some people have trouble establishing partners

### Include late sign ups

### Need closure on the process to prevent “loosing people”.

## Schedule - Establish common schedule or alternatively have “partner level schedule”

### Different schedules, e.g. Australia’s summer is our winter, time differences, etc., important to world wide collaboration.

## Lesson Plans - Offer common lesson plans and tools to make the partners successful, e.g. show how to use in the curriculum.

### Example, read “Nightmare in my closet”, cover up the monster pictures and then ask the kids to describe the monsters in the book without having seen them.  Then ask the kids why their descriptions ended up differently.

### Need a WebBoard or discussion group to share ideas.

### Creates a “Teacher’s lounge” or the ability to “observe” to determine how they can / will use it.

## Establish Communication - set up communication areas, WebBoard, Chat, mailing list, etc.

## Execution - Let them go, trouble shoot, FAQ, etc., answer the how do I?

## Product Completed

## Exchange Product

## Post Results - Post the results on the Web.

### Administrator does it

### Teacher writes the HTML

### Postal mail it

### Nobody does it

## Feedback from kids/teachers in other schools

### What was good?

### How do we improve?

### Know / Want / Learn

#### What do you know about Australia

#### What do you want to learn about Australia

#### What did we learn about Australia

## Show it Off - Show it all off, let the kids really get a look at it all.

# PARTICIPATING TEACHER:

## Find - Find the Project (see BBS in the Administration description)

## Interest - Decide if they are interested, do they have the skills, etc. to participate, understand the basic “flow” of the project and if it fits.

## Curriculum Fit - Will it fit in their curriculum (Links back to ideas on lesson plans in administration)

## How to Use - Figure out how they will use it as a vehicle and for what objectives.  Personalize it for their classroom.

## Sign up - Sign up and get a confirmation that they are in the project.

## Get a Partner - Get paired up with the schools that will be partnering.

## Communications Link - Establish a means and schedule of communication with the partners.

## Getting to Know Each Other - Exchange basic information about each other, the schools, the students, etc.

## Schedule - Determine if there will be a common project level schedule, or a partner level schedule, what are the key milestones.

## First Task / Draw - Execute the first task.  This is where trouble shooting comes in.

## Progress Status - Communicate status to be sure that all team members are making progress., good time for the kids to ask their questions from other content areas, virtual field trip via all the participants.

## Second Task / Describe

## Get the product in an exchangeable format

## Exchange - Exchange the product, post office, e-mail, fax, etc.

## Receive - How to receive and e.g. decompress the files

## Third Task / Read and Draw - Read the descriptions and draw the other persons monster.

## Communicating Status - Yes I’ve read your description and drawn the monster.

## Format - Format the messages as HTML, the images as JPEG or GIF

## Submit - Send the images and HTML

## Receive - Receive the product

## Present - Present the product to the participating students either through HTML or L-view (a GIF reader), or in paper.

### Many schools stop here because they have derived 80% of the value and they are running out of time, etc.

## Feedback - Get comments and feedback from kids, needs to be timely or they loose their interest.

## Format - Format their comments for exchange

## Exchange - Exchange their comments.

## Receive  - Receive the comments, unzip, etc.

## Present - Presenting the comments from the other students from the other schools.

# PARTICIPATING STUDENT:

## Kids real time chat - must be a fortress that can not be penetrated by others that are not part of it.

## Computer conferencing - e.g. monitored WebBoard

## Mailing list - Web based mailing list

## Process to establish key pals

# OBJECTS:

## Project Object

### Attributes

#### Educational objective

##### e.g. descriptive writing process, reading, different mini lessons such as punctuation, different parts of speech, e-mail

#### Vehicle

##### Tools using such as MYST

#### Outline of project flow

##### Steps that the students will be taken through

#### Directions for participating

##### Basic directions for how to do it

#### Group size

##### Number of schools and/or students desired in this project

#### Group attributes

##### Geography, number of schools, number of students, etc.

#### Geographic locations

##### Where from to identify zone and annual schedule problems, time constraints

#### Audience

##### What grade level

#### Timeline of project

#### List of required technology

##### e.g. e-mail, web access, I-phone, hardware, software, special programs (WebBoard, etc.), access speed required, chat

#### List of required computer skills

##### ability to send MIME mail, scan pictures, write HTML, support staff available, etc.

#### Cost to participate

#### Language

##### English vs Spanish, etc.

#### Description of project Web output

##### e.g. the two monster images and the one text description

### Methods

#### Collect and record the information

#### Check for completeness

#### Send it for evaluation

#### Confirm entry to submitter mirror data back to them

#### Feedback decision from committee to submitter

#### Determination of cost and fees

## Control  Object

### Attributes

#### List of objects to be controlled

#### Control sequence

#### Control logic (what if)

### Methods

#### Method to call objects

#### Method to decide on control logic

## Advertise Object

### Attributes

#### Advertisement

##### Composed from Project Object attributes

#### List of where to advertise

##### Chinese menu, BBS, Web Page, magazines, trade conventions, Educational departments (NYSED, BOCES, etc.)

#### Cost to advertise

#### Duration of advertisement

#### Associated advertisers

#### Fees to associated advertisers

### Methods

#### Creating the advertisement

#### Posting to the list of advertisers

#### Creation of the associated advertisements

## Sign up Object

### Attributes

#### Sign up date

##### Date on which an individual signs up

#### Sign up deadline

##### Last date by which anyone can sign up

#### Name of participant

#### E-mail of participant

#### Phone / Fax numbers

#### School/organization address

#### Verification of Project Object information

##### The information that demonstrates that a participant has the necessary attributes to be a part of the project, this links back to the Project Object

#### Number of students participating

#### Which session signing up for

### Methods

#### Creation of sign up form from Project Object

#### Collect and record data

## Grouping Object

### Attributes

#### Grouping attributes form Project Object and Sign up Object

### Methods

#### Searches all attributes of the all logged information

#### Sorts according to project criteria

#### Matching of Sign up Object attributes to Project Object attributes

#### Matching logic to pair potential candidates

#### If match fails then a method to revert to manual grouping

#### Notify the participants in each group of their grouping and/or fact that they have been put into the manual process - confirmation

## Community Center Object

### Attributes

#### List / directory of community members

#### List of community members online now

#### List of relevant Web sites (LivingPage)

#### Grade relevant MirroredDNS

#### Project relevant WebBoard

#### Chat sessions

#### Lounge WebBoard

#### All forms of communication

#### Mailing lists

#### FAQ for projects

#### FAQ for various software

#### FAQ for using the communication tools

#### FAQ for hardware

#### A hyperlinked list of tools, e.g. Web authoring tools

### Methods

#### Set up communications functions, both asynchronous and synchronous, ie. WebBoard and Chat, I-phone, etc.

## Project Web Output Builder Object

### Attributes

#### Project Web Output attributes from the Project Object

### Methods

#### Set of tools to post text, images, sound, video, chat sessions, etc.

#### Like MSN e-mail method of adding/deleting

## Feedback Object

### Attributes

#### Feedback text / comments

### Methods

#### Ability to send and/or post comments

## Reminder  Object

### Attributes

#### List of time driven reminders

#### List of event driven reminders

#### List of count driven reminders

### Methods

#### Ability to send reminder notice

#### Methods to sense time

#### Methods to sense events

#### Methods to sense counts

## Security  Object

### Attributes

#### Object it is to secure access to

#### Level of security, e.g. password, alias etc.

### Methods

#### Ability to restrict access

#### Ability to report attacks on access

#### Look at Kidlink for examples

## Billing Object

### Attributes

#### Project Object attributes

#### Sign up Object attributes

#### Billing attributes

### Methods

#### Ability to feed billing system