| Carrier World Wide Web Site Schedule Overview Prepared Jointly by Sage Marcom Inc., One World Interactive, and NPAC (as of 10/20/95) | Completion Time (Business Days) |
| --- | --- |
| A. Initial Project Meeting: | Done |
| B. Redefinition of Specs: | Done |
| C. Finalize Team Budgets: | Done |
| D. Issue Carrier PO to Team: | TBD |
| E. Content Resourcing/Concept Development/ Level I and II Flowcharting: | 20 days after OK of “D” |
| F. Review of Functional Elements: - Review of All Flowcharts: - Graphic Design Review: - Content Review: | 10-21 days after OK of “D” 30 days after OK of “D” 40 days after OK of “D” |
| G. Review of Prototype: | 10 days after OK of content review |
| H. Final Content Merger with Design/Add Navigation Tools & Links/Usability Testing & Final Proofing/ Internal Staging: | 9 days after OK of “G” |
| I. Host Site Ready | 5 days prior to launch |
| J. Site Upload & Internet Launch | 1day after OK of “H” |

Note: A detailed Gantt chart will be developed and Web-activated upon client approvals to proceed.  Included will be identification of all Team and client action items and approval requirements.